## Sheet1
8957 | Date | 2026-01-02
| SO# | P-037294 PO0000424758
| Customer | Eldridge Lumber & Hardware
| Address | 319 Marginal Way Portland, ME
| Tech Hours | 28
| Tech Names | 2026-01-05: Avery, Charlie, Travis, Seth ¦ 2026-01-06: Avery(8hrs), Charlie(8hr), Seth(8hrs)
| Job Complete | Yes
| Unit | Quantity | Notes
AERIAL CONSTRUCTION UNITS
04A100 - Aerial 12 Fiber Drop (price per foot included P-hanger, preforms and lags, fiber provided by FirstLight) | per ft | 260 | 2026-01-06: pulled new flat drop spanning two poles into building
04A100 - Install 5/16" Strand and pole hardware (includes strand/pole hardware in material pricing) (10M) | per ft | 0
04A100 - Install 5/16" Strand and pole hardware (without strand in material pricing but includes pole hardware) (10M) | per ft | 0
04A100 - Install 1/4" Strand and pole hardware (includes strand/pole hardware in material pricing) (6M) | per ft | 0
04A100 - Install 1/4" Strand and pole hardware (without strand in material pricing but includes pole hardware) (6M) | per ft | 0
04A100 - Re-sag plant (includes redresssing the pole…respace, shorten or lengthen lashing wire) | per span | 0
04A100 - Wreck out (includes all hardware, strand, fiber, and disposal) | per ft | 0
04A100 - Install/ supply 5/16" Down guy (includes appropriate hardware and 6' guard, includes strand) | per each | 0
04A100 - Install/ supply 5/16" Down guy (includes appropriate hardware and 6' guard, without strand) | per each | 0
04A100 - Install/ supply 5/16" Aerial guy (includes appropriate hardware and strand) | per each | 0
04A100 - Install/ supply 5/16" Aerial guy (includes appropriate hardware, without strand) | per each | 0
04A100 - Install/ supply 1/4" Down guy (includes appropriate hardware and 6' guard, includes strand) | per each | 0
04A100 - Install/ supply 1/4" Down guy (includes appropriate hardware and 6' guard, without strand) | per each | 0
04A100 - Install/ supply 1/4" Aerial guy (includes appropriate hardware and strand) | per each | 0
04A100 - Install/ supply 1/4" Aerial guy (includes appropriate hardware, without strand) | per each | 0
04A100 - Install/supply 5/16" sidewalk guy (includes appropriate hardware and 6' guard, includes strand) | per each | 0
04A100 - Install/ supply 5/16" sidewalk guy (includes appropriate hardware and 6' guard, without strand) | per each | 0
04A100 - Install/ supply 1/4" sidewalk guy (includes appropriate hardware and 6' guard, includes strand) | per each | 0
04A100 - Install/ supply 1/4" sidewalk guy (includes appropriate hardware and 6' guard, without strand) | per each | 0
04A100 - Install Power Vertical Bonds (includes all copper and hardware) | per each | 0
04A100 - Install Ground Rod (includes all copper and hardware) | per each | 0
04A100 - X-Arm Supply & Install (Fiberglass 12") | per each | 0
04A100 - X-Arm Supply & Install (Fiberglass 24") | per each | 0
04A100 - X-Arm Supply & Install (Fiberglass 36") | per each | 0
04A100 - Pole Transfer - Straight | per each | 0
04A100 - Pole Transfer - Curved | per each | 0
04A100 - Pole Transfer - Junction | per each | 0
04A100 - Pole Transfer - Dead End | per each | 0
04A100 - Pole Transfer - Four Way Junction or more | per each | 0
04A100 - Install Fiber 001 - 144 (fiber provided by FirstLight) | per ft | 0
04A100 - Install Fiber 145 - 288 (fiber provided by FirstLight) | per ft | 0
04A100 - Install Fiber 289 - 432 (fiber provided by FirstLight) | per ft | 0
04A100 - Install Fiber 433 - 864 (fiber provided by FirstLight) | per ft | 0
04A100 - Delash Only Up to 4 lashing wires | per ft | 0
04A100 - Relash Only | per ft | 0
04A100 - Delash / Relash | per ft | 0
UNDERGROUND UNITS
04A200 - Install Fiber In Conduit 1- 144f (price per foot, fiber provided by FirstLight) | per ft | 0
04A200 - Install Fiber In Conduit 145- 431f (price per foot, fiber provided by FirstLight) | per ft | 0
04A200 - Install Fiber In Conduit 432- 864f (price per foot, fiber provided by FirstLight) | per ft | 0
04A200 - Install Cable in Conduit Power Space Adder | per ft | 0
04A200 - UG Innerduct-Install 1 1/4" duct in conduit. (Innerduct provided by the contractor) | per ft/each | 0
04A200 - UG Innerduct-Install 3/4" duct in conduit. (Innerduct provided by the contractor) | per ft/each | 0
04A200 - UG Innerduct-Install 1/2" duct in conduit. (Innerduct provided by the contractor) | per ft/each | 0
04A200 - Install Innerduct in Conduit Power Space Adder | per ft/each | 0
04A200 - Install 2" 3 cell-Maxcell in Conduit. (Maxcell provided by contractor) | per ft/each | 0
04A200 - Install 2" 3 cell Maxcell in Conduit Power Space Adder. (Maxcell provided by contractor) | per ft/each | 0
04A200 - Rod & Rope & Mule tape (price per foot including detectable muletape) | per ft | 0
04A200 - Rod & Rope & Mule tape in Conduit Power Space Adder | per ft | 0
04A200 - Open Trench in Grass (Install 2" conduit or less) | per ft | 0
04A200 - Open Trench in Grass (Install greater than 2" up to 4" conduit) | per ft | 0
04A200 - Open Trench in Asphalt / Concrete (Price based on local restoration specifications-most likely a bid job) | per ft | 0
04A200 - Directional Drill (1) 2" conduit or less | per ft | 0
04A200 - Directional Drill Rock Adder | per ft | 0
04A200 - Supply/Install a 35' class 5 utility pole in earth | per each | 0
04A200 - Install Screw Anchor with poleset, 1" x 7' rod w/ triple eye, 10" helix | per each | 0
04A200 - Install Screw Anchor without poleset, 1" x 7' rod w/ triple eye, 10" helix | per each | 0
04A200 - Install Ledge Anchor/Pin with poleset, 30" Ledge Pin | per each | 0
04A200 - Install Ledge Anchor/Pin without poleset, 30" Ledge Pin | per each | 0
04A200 - Install 17x30x17 Fiberglass Hand Hole, 20K lb. cover rating (Firstlight will provide hand hole) | per each | 0
04A200 - Install 24x36x30 Cement Handhole w/locking cover, 20k lb cover rating (Firstlight will provide hand hole) | per each | 0
04A200 - Install Round 8" Fiberglass Fiber ped- Charles Industry BDG3 (Firstlight will provide ped) | per each | 0
04A200 - Install 6' copper ground rod in fiber ped or hand hole, this is so we can bond our shielded fiber/closure safely | per each | 0
04A200 - UnRack/Rack Telecom Manhole Splice | per each | 0
04A200 - UnRack/Rack Power Manhole Splice | per each | 0
04A200 - Pump (De-Water) Manhole | per each | 0
BUILDING UNITS - CONSTRUCTION
04A100 - Site Survey (PDF MOP prepared) | per each | 0
04A100 - Building Attachment | per each | 0
04A100 - Cleat cable to pole or building | per foot | 0
04A100 - Wall Bore Building Entry Wood/Brick/Block up to 4" | per each | 1 | 2026-01-06: Had to drill new hole into suite to get into the telco closet
04A100 - Interior Core Wood/Drywall all sizes | per each | 0
04A100 - Concrete Core 2" to 4" Wall/Floor includes fire stop | per each | 0
04A100 - Rod & Rope interior empty or occupied conduit including non-detectable muletape | per each | 0
04A100 - Install Interior Plenum Fiber (price per foot, fiber provided by FirstLight) | per ft | 250 | 2026-01-06: Pulled new 12ct plenum from MPOE to customer suite
04A100 - Install Interior 1" Plenum Duct (zip tied in crawl space, chase way, conduit or ceiling area) | per ft | 0
ADDITIONAL UNITS - CONSTRUCTION
04A300 - Police Detail (billed at cost plus 10% TBD by each Town) | total | 0
04B000 - Fiber Splicer (Including Labor, Equipment and Vehicle) | total | 0
04A100 - Two-man Construction Crew (Includes Labor, Equipment and Vehicle) | total | 0
04A100 - Supervisor ( Includes labor & Vehicle) | total | 0
04A300 - Flaggers (per each, per hour) | total | 0
04B000 - Per-Diem (if overnight travel is required) | per each | 0
03C100 - Set Up Fee (Jobs w/ Gross Value < $1,000 or > 75 mile radius from contractors office) | per each | 0
SPLICING UNITS
04B000 - Install Fiber Rack/Wall/Pole mount FDP and splice 6 fibers (FDP supplied by FirstLight) | per each | 0
04B000 - Install Fiber Rack/Wall/Pole mount FDP and splice 12 fibers (FDP supplied by FirstLight) | per each | 1 | 2026-01-05: 1 rack mount @ Dmarc
04B000 - Install/Supply backboard (contractor provides the plywood backboard) | per each | 1 | 2026-01-06: 1@customer location
04B000 - Enter Fiber FDP/Rack/Wall/Pole Mount/ONT/Cabinet (SPLICING/PATCHING STRANDS THRU ONLY) | per each | 0
04B000 - Install 6 pack w/pigtail in rackmount and splice 6 fibers (Provided by Firstlight) | per each | 0
04B000 - Install 12 pack w/pigtail in rackmount and splice 12 fibers (Provided by Firstlight) | per each | 0
04B000 - Install SNAP (Residential fiber closure) | per each | 0
04B000 - Open / Split buffer tube in existing SNAP | per each | 1 | 2026-01-06: 1@customer location
04B000 - Prep additional fiber into SNAP | per each | 1 | 2026-01-05: 1 @ location 1
04B000 - Enter SNAP (SPLICING/PATCHING STRANDS THRU ONLY) | per each | 8 | 2026-01-06: Chasing down a broken fiber, had to enter the snaps leading to customer location per engineer
04B000 - Coyote Drop Enclosure(DTC-101) (For Fiber Drop Restoration) (Provided by contractor) | per each | 0
04B000 - Install additional fiber tail into fiber closure (Tyco's, Coyotes & Raychems) | per each | 0
04B000 - Prep/Install Ring Cut Splice Closure (Tyco C or D) | per each | 0
04B000 - Prep/Install Butt Splice Closure (Tyco C or D) | per each | 0
04B000 - Prep/Install end splice closure on a single fiber tail to feed a drop (Tyco C or D) | per each | 0
04B000 - Open / Split Buffer Tube in existing fiber closure (Tyco's, Coyotes & Raychems) | per each | 0
04B000 - Add snowshoe (adding single snowshoe to exisitng slack loop or splice) (17" snowshoe provided by contractor) | per each | 0
04B000 - Enter Tyco/Coyote/Raychem or equivalent-(Splice prep charge less than 12 fibers spliced, anything over 12, the entry fee charge is waved.) | per each | 0
04A100 - Strap Out Splice Closure (Deltec / Heads) | per each | 0
04A100 - De/Re Splice Enclosure | per each | 0
04B000 - Fiber Splices 1-12 | per fiber | 6 | 2026-01-05: 1 @ location 1 ¦ 2026-01-06: 2@ broken fiber locations, 3@ customer location
04B000 - Fiber Splices 13-36 | per fiber | 0
04B000 - Fiber Splices 37-60 | per fiber | 0
04B000 - Fiber Splices 61-72 | per fiber | 0
04B000 - Fiber Splices 73-96 | per fiber | 0
04B000 - Fiber Splices 97-144 | per fiber | 0
04B000 - Fiber Splices >145 | per fiber | 0
04B000 - 1-36 Ribbon (1 to 3 ribbon, price per ribbon) | per ribbon | 0
04B000 - 36-72 Ribbon (3 to 6 ribbon, price per ribbon) | per ribbon | 0
04B000 - > 72 Ribbon (price per ribbon) | per ribbon | 0
04B000 - Ribbonizing/De-ribbonizing per ribbon | per ribbon | 0
SPLICING MATERIAL
Materials - 04B000 - Add Coyote Pole Mount | per each | 0
Materials - 04D100 - Add closure Tyco C | per each | 0
Materials - 04D100 - Add closure Tyco D | per each | 0
Materials - 04D100 - Add closure Tyco 600 | per each | 0
Materials - 04B000 - Add Corning Snap Closure | per each | 0
Materials - 04D100 - Add tray Tyco C | per each | 0
Materials - 04D100 - Add tray Tyco D or 600 | per each | 0
Materials - 04B000 - Add tray SNAP | per each | 0
Materials - 04D100 - Add Slack Basket Tyco C | per each | 0
Materials - 04D100 - Add Slack Basket Tyco D or 600 | per each | 0
Materials - 04D100 - Add Mounting Bracket Tyco 600 | per each | 0
Materials - 04D100 - Add Mounting Bracket Tyco D or C | per each | 0
Materials - 04D100 - Add Gel drop seal kit for Tyco | per each | 0
Materials - 04B000 - Add single snowshoe | per each | 0
Materials - Rack Mount FDP | per each | 1 | 2026-01-06: 1@ customer location telco closet
Materials - Wall Mount FDP | per each | 1 | 2026-01-06: 1@customer location MPOE
Materials - Drop Cable Deadend | per each | 3 | 2026-01-06: 2@midle pole, 1@ roadside pole
Materials - 1/4" Guy Grip Deadend | per each | 0
Materials - 5/16" Guy Grip Deadend | per each | 0
Materials - ADSS Limited Tension Deadend w/Thimble Clevis & Extension Link | per each | 0
Materials - ADSS Light Tension Deadend | per each | 0
Materials - ADSS Stand-off Bracket | per each | 0
Materials - ADSS Tangent Clamp | per each | 0
BUILDING UNITS - SPLICING
04A100 - Site Survey (PDF MOP prepared) | per each | 0
04A100 - Building Attachment | per each | 0
04A100 - Cleat cable to pole or building | per foot | 0
04A100 - Wall Bore Building Entry Wood/Brick/Block up to 4" | per each | 0
04A100 - Interior Core Wood/Drywall all sizes | per each | 0
04A100 - Concrete Core 2" to 4" Wall/Floor includes fire stop | per each | 0
04A100 - Rod & Rope interior empty or occupied conduit including non-detectable muletape | per each | 0
04A100 - Install Interior Plenum Fiber (price per foot, fiber provided by FirstLight) | per ft | 0
04A100 - Install Interior 1" Plenum Duct (zip tied in crawl space, chase way, conduit or ceiling area) | per ft | 0
ADDITIONAL UNITS - SPLICING
04A300 - Police Detail (billed at cost plus 10% TBD by each Town) | total | 0
04B000 - Fiber Splicer (Including Labor, Equipment and Vehicle) | total | 18 | 2026-01-05: 2 techs @ 1 hour a piece Engineering with patch work getting tone moved. ¦ 2026-01-06: 2techs @8hrs trying to chase down a broken fiber, called engineer to try and find us location where it would be broken, ended up trying to change port assignments as well with no luck on the new port assignment, swapped ports back to the original assigned port, found the break and could make the pathway complete
04A100 - Two-man Construction Crew (Includes Labor, Equipment and Vehicle) | total | 0
04A100 - Supervisor ( Includes labor & Vehicle) | total | 0
04A300 - Flaggers (per each, per hour) | total | 0
04B000 - Per-Diem (if overnight travel is required) | per each | 0
03C100 - Set Up Fee (Jobs w/ Gross Value < $1,000 or > 75 mile radius from contractors office) | per each | 0