## Sheet1
8957 | Date | 2026-04-13
| SO# | 207622-002 PO0000427640
| Customer | VERIZON WIRELESS
| Address | 1 Robert Stevens Dr Pole #9.9 York, ME
| Tech Hours | 40
| Tech Names | 2026-04-22: Austin Ridlon 17, Chris Marston 17 ¦ 2026-04-23: N/A ¦ 2026-04-24: Avery(1hr)Seth(1hr) ¦ 2026-04-24: Austin Ridlon, Chris Marston ¦ 2026-04-28: N/A
| Job Complete | Yes
| Unit | Quantity | Notes
AERIAL CONSTRUCTION UNITS
04A100 - Aerial 12 Fiber Drop (price per foot included P-hanger, preforms and lags, fiber provided by FirstLight) | per ft | 0
04A100 - Install 5/16" Strand and pole hardware (includes strand/pole hardware in material pricing) (10M) | per ft | 0
04A100 - Install 5/16" Strand and pole hardware (without strand in material pricing but includes pole hardware) (10M) | per ft | 0
04A100 - Install 1/4" Strand and pole hardware (includes strand/pole hardware in material pricing) (6M) | per ft | 3062 | 2026-04-22: OTC Owned
04A100 - Install 1/4" Strand and pole hardware (without strand in material pricing but includes pole hardware) (6M) | per ft | 0
04A100 - Re-sag plant (includes redresssing the pole…respace, shorten or lengthen lashing wire) | per span | 0
04A100 - Wreck out (includes all hardware, strand, fiber, and disposal) | per ft | 0
04A100 - Install/ supply 5/16" Down guy (includes appropriate hardware and 6' guard, includes strand) | per each | 0
04A100 - Install/ supply 5/16" Down guy (includes appropriate hardware and 6' guard, without strand) | per each | 0
04A100 - Install/ supply 5/16" Aerial guy (includes appropriate hardware and strand) | per each | 0
04A100 - Install/ supply 5/16" Aerial guy (includes appropriate hardware, without strand) | per each | 0
04A100 - Install/ supply 1/4" Down guy (includes appropriate hardware and 6' guard, includes strand) | per each | 0
04A100 - Install/ supply 1/4" Down guy (includes appropriate hardware and 6' guard, without strand) | per each | 1 | 2026-04-22: P.1
04A100 - Install/ supply 1/4" Aerial guy (includes appropriate hardware and strand) | per each | 0
04A100 - Install/ supply 1/4" Aerial guy (includes appropriate hardware, without strand) | per each | 1 | 2026-04-22: P.82
04A100 - Install/supply 5/16" sidewalk guy (includes appropriate hardware and 6' guard, includes strand) | per each | 0
04A100 - Install/ supply 5/16" sidewalk guy (includes appropriate hardware and 6' guard, without strand) | per each | 0
04A100 - Install/ supply 1/4" sidewalk guy (includes appropriate hardware and 6' guard, includes strand) | per each | 0
04A100 - Install/ supply 1/4" sidewalk guy (includes appropriate hardware and 6' guard, without strand) | per each | 0
04A100 - Install Power Vertical Bonds (includes all copper and hardware) | per each | 9
04A100 - Install Ground Rod (includes all copper and hardware) | per each | 0
04A100 - X-Arm Supply & Install (Fiberglass 12") | per each | 0
04A100 - X-Arm Supply & Install (Fiberglass 24") | per each | 0
04A100 - X-Arm Supply & Install (Fiberglass 36") | per each | 0
04A100 - Pole Transfer - Straight | per each | 0
04A100 - Pole Transfer - Curved | per each | 0
04A100 - Pole Transfer - Junction | per each | 0
04A100 - Pole Transfer - Dead End | per each | 0
04A100 - Pole Transfer - Four Way Junction or more | per each | 0
04A100 - Install Fiber 001 - 144 (fiber provided by FirstLight) | per ft | 3962 | 2026-04-24: preterm cable
04A100 - Install Fiber 145 - 288 (fiber provided by FirstLight) | per ft | 0
04A100 - Install Fiber 289 - 432 (fiber provided by FirstLight) | per ft | 0
04A100 - Install Fiber 433 - 864 (fiber provided by FirstLight) | per ft | 0
04A100 - Delash Only Up to 4 lashing wires | per ft | 0
04A100 - Relash Only | per ft | 0
04A100 - Delash / Relash | per ft | 0
UNDERGROUND UNITS
04A200 - Install Fiber In Conduit 1- 144f (price per foot, fiber provided by FirstLight) | per ft | 0
04A200 - Install Fiber In Conduit 145- 431f (price per foot, fiber provided by FirstLight) | per ft | 0
04A200 - Install Fiber In Conduit 432- 864f (price per foot, fiber provided by FirstLight) | per ft | 0
04A200 - Install Cable in Conduit Power Space Adder | per ft | 0
04A200 - UG Innerduct-Install 1 1/4" duct in conduit. (Innerduct provided by the contractor) | per ft/each | 0
04A200 - UG Innerduct-Install 3/4" duct in conduit. (Innerduct provided by the contractor) | per ft/each | 0
04A200 - UG Innerduct-Install 1/2" duct in conduit. (Innerduct provided by the contractor) | per ft/each | 0
04A200 - Install Innerduct in Conduit Power Space Adder | per ft/each | 0
04A200 - Install 2" 3 cell-Maxcell in Conduit. (Maxcell provided by contractor) | per ft/each | 0
04A200 - Install 2" 3 cell Maxcell in Conduit Power Space Adder. (Maxcell provided by contractor) | per ft/each | 0
04A200 - Rod & Rope & Mule tape (price per foot including detectable muletape) | per ft | 0
04A200 - Rod & Rope & Mule tape in Conduit Power Space Adder | per ft | 0
04A200 - Open Trench in Grass (Install 2" conduit or less) | per ft | 0
04A200 - Open Trench in Grass (Install greater than 2" up to 4" conduit) | per ft | 0
04A200 - Open Trench in Asphalt / Concrete (Price based on local restoration specifications-most likely a bid job) | per ft | 0
04A200 - Directional Drill (1) 2" conduit or less | per ft | 0
04A200 - Directional Drill Rock Adder | per ft | 0
04A200 - Supply/Install a 35' class 5 utility pole in earth | per each | 0
04A200 - Install Screw Anchor with poleset, 1" x 7' rod w/ triple eye, 10" helix | per each | 0
04A200 - Install Screw Anchor without poleset, 1" x 7' rod w/ triple eye, 10" helix | per each | 0
04A200 - Install Ledge Anchor/Pin with poleset, 30" Ledge Pin | per each | 0
04A200 - Install Ledge Anchor/Pin without poleset, 30" Ledge Pin | per each | 0
04A200 - Install 17x30x17 Fiberglass Hand Hole, 20K lb. cover rating (Firstlight will provide hand hole) | per each | 0
04A200 - Install 24x36x30 Cement Handhole w/locking cover, 20k lb cover rating (Firstlight will provide hand hole) | per each | 0
04A200 - Install Round 8" Fiberglass Fiber ped- Charles Industry BDG3 (Firstlight will provide ped) | per each | 0
04A200 - Install 6' copper ground rod in fiber ped or hand hole, this is so we can bond our shielded fiber/closure safely | per each | 0
04A200 - UnRack/Rack Telecom Manhole Splice | per each | 0
04A200 - UnRack/Rack Power Manhole Splice | per each | 0
04A200 - Pump (De-Water) Manhole | per each | 0
BUILDING UNITS - CONSTRUCTION
04A100 - Site Survey (PDF MOP prepared) | per each | 0
04A100 - Building Attachment | per each | 0
04A100 - Cleat cable to pole or building | per foot | 25
04A100 - Wall Bore Building Entry Wood/Brick/Block up to 4" | per each | 0
04A100 - Interior Core Wood/Drywall all sizes | per each | 0
04A100 - Concrete Core 2" to 4" Wall/Floor includes fire stop | per each | 0
04A100 - Rod & Rope interior empty or occupied conduit including non-detectable muletape | per each | 0
04A100 - Install Interior Plenum Fiber (price per foot, fiber provided by FirstLight) | per ft | 0
04A100 - Install Interior 1" Plenum Duct (zip tied in crawl space, chase way, conduit or ceiling area) | per ft | 0
ADDITIONAL UNITS - CONSTRUCTION
04A300 - Police Detail (billed at cost plus 10% TBD by each Town) | total | 0
04B000 - Fiber Splicer (Including Labor, Equipment and Vehicle) | total | 0
04A100 - Two-man Construction Crew (Includes Labor, Equipment and Vehicle) | total | 0
04A100 - Supervisor ( Includes labor & Vehicle) | total | 0
04A300 - Flaggers (per each, per hour) | total | 34 | 2026-04-22: 2 flaggers at 17 hours ea
04B000 - Per-Diem (if overnight travel is required) | per each | 0
03C100 - Set Up Fee (Jobs w/ Gross Value < $1,000 or > 75 mile radius from contractors office) | per each | 0
SPLICING UNITS
04B000 - Install Fiber Rack/Wall/Pole mount FDP and splice 6 fibers (FDP supplied by FirstLight) | per each | 1
04B000 - Install Fiber Rack/Wall/Pole mount FDP and splice 12 fibers (FDP supplied by FirstLight) | per each | 0
04B000 - Install/Supply backboard (contractor provides the plywood backboard) | per each | 0
04B000 - Enter Fiber FDP/Rack/Wall/Pole Mount/ONT/Cabinet (SPLICING/PATCHING STRANDS THRU ONLY) | per each | 0
04B000 - Install 6 pack w/pigtail in rackmount and splice 6 fibers (Provided by Firstlight) | per each | 0
04B000 - Install 12 pack w/pigtail in rackmount and splice 12 fibers (Provided by Firstlight) | per each | 0
04B000 - Install SNAP (Residential fiber closure) | per each | 0
04B000 - Open / Split buffer tube in existing SNAP | per each | 0
04B000 - Prep additional fiber into SNAP | per each | 0
04B000 - Enter SNAP (SPLICING/PATCHING STRANDS THRU ONLY) | per each | 0
04B000 - Coyote Drop Enclosure(DTC-101) (For Fiber Drop Restoration) (Provided by contractor) | per each | 0
04B000 - Install additional fiber tail into fiber closure (Tyco's, Coyotes & Raychems) | per each | 0
04B000 - Prep/Install Ring Cut Splice Closure (Tyco C or D) | per each | 0
04B000 - Prep/Install Butt Splice Closure (Tyco C or D) | per each | 0
04B000 - Prep/Install end splice closure on a single fiber tail to feed a drop (Tyco C or D) | per each | 1
04B000 - Open / Split Buffer Tube in existing fiber closure (Tyco's, Coyotes & Raychems) | per each | 0
04B000 - Add snowshoe (adding single snowshoe to exisitng slack loop or splice) (17" snowshoe provided by contractor) | per each | 0
04B000 - Enter Tyco/Coyote/Raychem or equivalent-(Splice prep charge less than 12 fibers spliced, anything over 12, the entry fee charge is waved.) | per each | 0
04A100 - Strap Out Splice Closure (Deltec / Heads) | per each | 1 | 2026-04-24: 1@location 2
04A100 - De/Re Splice Enclosure | per each | 0
04B000 - Fiber Splices 1-12 | per fiber | 6 | 2026-04-24: 6@location 2
04B000 - Fiber Splices 13-36 | per fiber | 0
04B000 - Fiber Splices 37-60 | per fiber | 0
04B000 - Fiber Splices 61-72 | per fiber | 0
04B000 - Fiber Splices 73-96 | per fiber | 0
04B000 - Fiber Splices 97-144 | per fiber | 0
04B000 - Fiber Splices >145 | per fiber | 0
04B000 - 1-36 Ribbon (1 to 3 ribbon, price per ribbon) | per ribbon | 0
04B000 - 36-72 Ribbon (3 to 6 ribbon, price per ribbon) | per ribbon | 0
04B000 - > 72 Ribbon (price per ribbon) | per ribbon | 0
04B000 - Ribbonizing/De-ribbonizing per ribbon | per ribbon | 0
SPLICING MATERIAL
Materials - 04B000 - Add Coyote Pole Mount | per each | 0
Materials - 04D100 - Add closure Tyco C | per each | 1
Materials - 04D100 - Add closure Tyco D | per each | 0
Materials - 04D100 - Add closure Tyco 600 | per each | 0
Materials - 04B000 - Add Corning Snap Closure | per each | 0
Materials - 04D100 - Add tray Tyco C | per each | 1
Materials - 04D100 - Add tray Tyco D or 600 | per each | 0
Materials - 04B000 - Add tray SNAP | per each | 0
Materials - 04D100 - Add Slack Basket Tyco C | per each | 0
Materials - 04D100 - Add Slack Basket Tyco D or 600 | per each | 0
Materials - 04D100 - Add Mounting Bracket Tyco 600 | per each | 0
Materials - 04D100 - Add Mounting Bracket Tyco D or C | per each | 0
Materials - 04D100 - Add Gel drop seal kit for Tyco | per each | 0
Materials - 04B000 - Add single snowshoe | per each | 0
Materials - Rack Mount FDP | per each | 0
Materials - Wall Mount FDP | per each | 0
Materials - Drop Cable Deadend | per each | 0
Materials - 1/4" Guy Grip Deadend | per each | 0
Materials - 5/16" Guy Grip Deadend | per each | 0
Materials - ADSS Limited Tension Deadend w/Thimble Clevis & Extension Link | per each | 0
Materials - ADSS Light Tension Deadend | per each | 0
Materials - ADSS Stand-off Bracket | per each | 0
Materials - ADSS Tangent Clamp | per each | 0
BUILDING UNITS - SPLICING
04A100 - Site Survey (PDF MOP prepared) | per each | 0
04A100 - Building Attachment | per each | 0
04A100 - Cleat cable to pole or building | per foot | 0
04A100 - Wall Bore Building Entry Wood/Brick/Block up to 4" | per each | 0
04A100 - Interior Core Wood/Drywall all sizes | per each | 0
04A100 - Concrete Core 2" to 4" Wall/Floor includes fire stop | per each | 0
04A100 - Rod & Rope interior empty or occupied conduit including non-detectable muletape | per each | 0
04A100 - Install Interior Plenum Fiber (price per foot, fiber provided by FirstLight) | per ft | 0
04A100 - Install Interior 1" Plenum Duct (zip tied in crawl space, chase way, conduit or ceiling area) | per ft | 0
ADDITIONAL UNITS - SPLICING
04A300 - Police Detail (billed at cost plus 10% TBD by each Town) | total | 0
04B000 - Fiber Splicer (Including Labor, Equipment and Vehicle) | total | 0
04A100 - Two-man Construction Crew (Includes Labor, Equipment and Vehicle) | total | 0
04A100 - Supervisor ( Includes labor & Vehicle) | total | 0
04A300 - Flaggers (per each, per hour) | total | 0
04B000 - Per-Diem (if overnight travel is required) | per each | 0
03C100 - Set Up Fee (Jobs w/ Gross Value < $1,000 or > 75 mile radius from contractors office) | per each | 0